Regional Consortia School Improvement Grant Spending Plan 2022 -2023

School: Johnston C.P. School School Number:

Headteacher: Mr R .Williams (Acting Headteacher) Chair of Governors: Mrs. Tracey Young

|  |  |  |
| --- | --- | --- |
| Code  |   | Objectives  |
| A  | Objective 1  | Raise standards of Oracy and Welsh across the school and introduce an international language (French) to all learners.  |
| B  | Objective 2  | Design, develop and implement the curriculum in Relationships and Sexuality Education (RSE) and Religion, Values and Ethics (RVE) tailored to needs and understanding of the pupils of Johnston Primary School.  |
| C  | Objective 3  | Assessment for learning and assessing learning is used to improve learner effectiveness, including improving pupils’ independent and metacognitive learning skills. Whole-school focus on assessing learning within the Curriculum for Wales.  |

Schools will need to use the code to identify which objective the action is addressing

 These should be consistent with your SDP Funding - 2022/23 - £13, 869.00 Details of expenditure

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| EIG Objective (Could be more than one)  |  | Actions to be taken  | School Lead  | Start  | End  | Resource (including staff costs)  | RAG  |
| C  | • • •  | Opportunity for our early years team to attend training linked to the implementing curriculum for Wales. Staff will attend training and share information with the rest of the support staff team. Staff will evaluate how they use manipulatives to provide children with the opportunity to develop an understanding of different concepts.   | DHT HT         Subject leads and SLT.  | Oct 222  | July 2024  | £300  |   |
|  |  |   |  |  |  |  |  |
| C and A | • • • •  | To introduce and monitor Voice 21 in progression steps one and two. To support staff to develop authentic contexts for pupils to use oracy skills. To monitor and introduce Curriclulum for Wales in Progression Step One. To ensure that systems support pupils to make strong progress in reading and that accurate base line information is used to target support. To mentor and guide the development of teaching and learning in progression steps one and two.  | C.R. SLT  | Oct 22  | July  | £13,568.49  |   |

Monitoring and Evaluation

Actual outcomes

Evaluation and Way Forward